## Indicative Examples
Indicative Size |  | SMALL | MEDIUM | LARGE | EXTRA LARGE | Team Composition
Weeks- LOW |  | 4 | 10 | 16 | 26 | Delivery Manager - 1 (Part Time) Appian Architect - 1 (Part Time) Technical Lead - 1 Level 2 (Full Time) Designer1 - 1 Exp. Level 1 (Full Time) Designer 2 - 1 Level 1 Note: Experienced Level 1 - designer with Level 1 certification and multiple delivered projects.
Weeks - HIGH |  | 8 | 14 | 24 | +
Project Examples | Summary desciption of a typical project, by size | No integrations and development of 10 - 15 non-complex user stories with limited data modeling and reporting. Usually replacing a manual system and/or process, rather than legacy technology. Examples would be support for simple department workflows such as performance reviews or requests for approvals. | One or two low risk integrations with development of 40 - 60 user stories with 10 - 15 being of medium complexity. Usually replacing a standalone legacy system and/or process. Examples would be medium complexity department workflows such as selecting, reviewing, approving and finalizing a contract or managing HR on boarding. | Three to five integrations with one or two being complex with development of 70 - 100 user stories with 15 - 30 being of medium to high complexity. Usually replacing a legacy system and/or multiple processes. Examples would be complex multi-department workflows such as managing the entire Procure to Pay process or developing a fully integrated knowledge / decision management tool. | Five or more integrations with three complex with development of 250 - 350 user stories with 80 -100 being of medium to high complexity. Usually involves a complete replatforming of a legacy technology and many processes. Examples would be replacement of an existing large COTS application or the build out of an entire program of small to medium applications to drive a rapid transformation effort.
Example Project Estimation Factors by Size |  | Note: The ranges for each factor below are representative. Actual complexity ranges can vary based on size/complexity of each unit. (e.g. A project requiring 6 complex User Forms might represent the same effort as a project requiring 10 simple User Forms). Therefore all ranges are based on standard/basic components.
Process | Number of Process Steps | • 6-8 Steps • Small number of Exception Paths • 3-4 Roles | • 8-16 Steps • Small number of Exception Paths • 5-6 Roles | • 16-24 Steps • Significant number of Exception Paths • 6+ Roles | • 24-50 Steps • 2 -3 Discrete Domains with Significant number of Exception Paths • 10+ Roles
Number of Exception Paths
Number of User/Roles/Actors
| Clearly defined, documented and understood Process Steps | • Clearly defined and understood Target Process | • 2-3 process refinement iterations required for Process Clarification | • 4-5 process refinement iterations required for Process Clarification | • 6 - 8 process refinement iterations required for Process Clarification
Defined Process Stability
Integrations | Number of Integratable Systems | • 0-1 Systems | • 2-3 Systems | • 3-5 Systems | • 5+ Systems
User Interface | Number of User Forms/Reports | • 6-8 User Forms • 3-4 Reports | • 9-12 User Forms • 5-8 Reports | • 13-15 User Forms • 9-15 Reports | • 16 - 20 User Forms • 16 - 20 Reports
| Level of Form Complexity | • Simple Forms and Reports | • Medium Complexity | • Heavily Detailed Screens and Reports | • 2 -3 Discrete Domains with Involved Screens and Reports
Security | Complexity of requirements | • 2-4 different roles • Open access to all records and functionality • Appian security, single authentication method | • 4-6 different roles • 1-2 records accessable by few roles • Access to some functionality limited • Appian security, single authentication method | • 6-8 different roles • Most record access limited to specific roles • Most functionaly access limited to specific roles • Document level access requirements • Appian security, single authentication method | • Over 8 different roles • Most record access limited to specific roles • Most functionaly access limited to specific roles • Document level access requirements • Appian security with external lookups for additional security constraints • Multiple authentication methods
Business Rules | Rules Complexity | • Simple Forms with Minimal Customization | • Some Customization of Rules and Logic | • Complex Rules and Significant Customization | • 2 -3 Discrete Domains with Complex Rules and Significant Customization
Reports | Number and Complexity of System Generated Outputs (e.g. documents) and/or Reports | • 0-1 Outputs/Reports | • 2-3 Outputs/Reports | • 3-5 Outputs/Reports | • 5+ Outputs/Reports
Project Team | Description of typical team structure for sizes | Little to no coordination required with external development teams. | Coordination required with 1-2 external teams. | Coordination required with 3-4 external teams and/or significant dependencies across teams. | Coordination required with 5+ external teams and/or significant dependencies across teams.